## Growing Schedule
Growing Schedule
AT RISK | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
| Growth Start |  | Not Started |  | 2022-05-12
| Sawdust Treatment |  | Not Started |  | 2022-04-14 | 2022-05-12 | 28
| Agaricus Augustus |  | Not Started |  | 2022-05-12 | 2022-06-23 | 42
| Spawn Run |  | Not Started |  | 2022-05-13 | 2022-06-01 | 19
| Primordia Formation |  | Not Started |  | 2022-06-01 | 2022-06-16 | 15
| Fruiting |  | Not Started |  | 2022-06-16 | 2022-06-23 | 7
| Agaricus arvensis |  | Not Started |  | 2022-05-12 | 2022-06-23 | 42
| Spawn Run |  | Not Started |  | 2022-05-13 | 2022-06-01 | 19
| Primordia Formation |  | Not Started |  | 2022-06-01 | 2022-06-16 | 15
| Fruiting |  | Not Started |  | 2022-06-16 | 2022-06-23 | 7
| Hericium |  | Not Started |  | 2022-05-12 | 2022-06-04 | 23
| Spawn Run |  | Not Started |  | 2022-05-13 | 2022-05-25 | 12
| Primordia Formation |  | Not Started |  | 2022-05-25 | 2022-05-30 | 5
| Fruiting |  | Not Started |  | 2022-05-30 | 2022-06-04 | 5
| Pleurotus (ostreatus?) |  | Not Started |  | 2022-05-12 | 2022-06-10 | 29
| Spawn Run |  | Not Started |  | 2022-05-13 | 2022-05-29 | 16
| Primordia Formation |  | Not Started |  | 2022-05-29 | 2022-06-03 | 5
| Fruiting |  | Not Started |  | 2022-06-03 | 2022-06-10 | 7
| Coprinus comatus |  | Not Started |  | 2022-05-12 | 2022-06-16 | 35
| Spawn Run |  | Not Started |  | 2022-05-13 | 2022-05-27 | 14
| Primordia Formation |  | Not Started |  | 2022-05-27 | 2022-06-09 | 14
| Fruiting |  | Not Started |  | 2022-06-09 | 2022-06-16 | 7
| Pisolithus (microcarpus?) |  | Not Started |  | 2022-05-12 | 2022-06-23 | 42
| Spawn Run |  | Not Started |  | 2022-05-13 | 2022-06-01 | 19
| Primordia Formation |  | Not Started |  | 2022-06-01 | 2022-06-16 | 15
| Fruiting |  | Not Started |  | 2022-06-16 | 2022-06-23 | 7
| SRUG1 - Stropharia rugoso-annulata |  | Not Started |  | 2022-05-12 | 2022-07-21 | 70
| Spawn Run |  | Not Started |  | 2022-05-13 | 2022-06-17 | 35
| Primordia Formation |  | Not Started |  | 2022-06-17 | 2022-07-07 | 20
| Fruiting |  | Not Started |  | 2022-07-07 | 2022-07-21 | 14
| LEDO2 - Lentinula edodes - Cold Outdoor |  | Not Started |  | 2022-05-12 | #REF! | #REF!
| Spawn Run |  | Not Started |  | 2022-05-13 | #REF! | #REF!
| Primordia Formation |  | Not Started |  | #REF! | #REF! | #REF!
| Fruiting |  | Not Started |  | #REF! | #REF! | #REF!
| AAUR1 - Auricularia auricula - Wood Ear - Wild type, SC |  | Not Started |  | 2022-05-12 | 2022-06-30 | 49
| Spawn Run |  | Not Started |  | 2022-05-13 | 2022-06-13 | 31
| Primordia Formation |  | Not Started |  | 2022-06-13 | 2022-06-23 | 10
| Fruiting |  | Not Started |  | 2022-06-23 | 2022-06-30 | 7
Formulas:
START DATE = [END DATE, row below]
START DATE = [START DATE, row above] + 1
END DATE = [START DATE]+[DURATION in days]
END DATE = [START DATE]+19

## Monthly Deliverables
Month: | Main Tasks:
April | Conduct grain spawn experiment
Set up growth chamber (when available)
Treat Sawdust
May | Assemble experimental units
Start cultivation in growth chambers
Narrow list of journals to potentially publish in
June | Continue Cultivation
Collect data on repeated flushes
Edit paper into journal format
Contact potential stakeholders about holding workshops
July | Continue Cultivation
Contact journals about publication

## Growth Conditions
[6 empty] | Spawn Run: |  |  | Primordia Formation: |  |  | Fruiting:
Species: | Refference | Agars | Technique | Substrates: | Casing Used: | Temperature (C) | Time (Days) | Humidity (%) | Temperature (C) | Time (days) | Humidity | Temperature (C) | Time (days) | Humidity | Time to first harvest (days) | Notes:
Agaricus augustus | (Beyer 2017) , (Stamets 2000) | MYPA | Trays | Pre-composted wood (Beyer 2017, Stamets 2000) | Yes | 23 to 25 | 18 to 20 | 95 to 100 (Stamets 200), Keep high (Beyer 2017) | 16 to 18 | 12 to 18 | 95 - 100 | 16 to 18 | 4 to 7 | 85 - 95 | 34 - 45 | Used information from the closely related A. brunnescens
Agaricus arvensis |  |  | Trays |  | Yes | Same as above |  |  | Same as above |  |  | Same as above |  |  |  | Not cultivated, but closely related to A. augustus
Hericium americanum (?) | (Sokól et al. 2015),(Stamets, 2000) | MYPA, PDYA, DFA | Bag, logs | Sawdust from hardwoods is preferred, although pine colonized by other species first may also be used. (Sokol et al., 2015) |  | 21 to 24 | 10 to 14 | 95 - 100 | 10 to 15.6 | 3 to 5 | 95 - 100 | 18 to 24 | 4 to 5 | 90 - 95 | 17 - 24
Pleurotus (ostreatus?) | (Sánchez 2004), (Stamets 2000) | MYPA, PDYA, DFA | Bag | Hardwoods, straw, paper. Not a picky species. |  | 24 to 29 | 12 to 21 | 85 - 95 | 10 to 15.6 | 3 to 5 | 95 - 100 | 10 to 21 | 4 to 7 | 85 - 90 | 21 - 34
Pisolithus (microcarpus?) | (Rossi & Oliveira 2011) |  |  |  |  | 25±1
Coprinus comatus | (Jang et al. 2009), (Stamets 2000) | MYP | Bag, Beds, Trays | Prefers growing on straw and manure mixtures. Can also work with paper. Peat-moss casing soil (Stamets 2000) | Yes | 23 to 26 | 12 to 14 | 95 - 100 | 16 to 21 | 12 to 15 | 95 - 100 | 18 to 24 | 5 to 7 | 80 - 90 | 29-36
Ganoderma (applanatum?) | (Woo-sik et al. 2009) |  | Bags, logs | Hardwood sawdust. |  | 25 to 30 | 10 to 12 | 95 - 100 | 18 to 24 | 21 to 27 | 95 - 100 | 21 to 27 | 60 | 90 95 | 91 - 99 | Data for Ganoderma lucidum
SRUG1 - Stropharia rugoso-annulata | (Stamets 2000) |  | Bag, Beds, Trays | Sawdust, straw | Yes | 21 to 27 | 25 to 45 | 95 - 100 | 10 to 16 | 14 to 21 | 95 - 98 | 16 to 21 | 7 to 14 | 90 - 95 | 46 - 80
LEDO2 - Lentinula edodes - Cold Outdoor | (Stamets 2000) |  | Bag, logs | Hardwoods, sawdust, straw. |  | 21 to 27 | 35 to 70 (Strain dependent) | 95 - 100 | 10 to 16 | 5 to 7 | 95 - 100 | 16 to 18 | 5 to 8 | 60 - 80 | 45 - 85
AAUR1 - Auricularia auricula - Wood Ear - Wild type, SC | (Stamets 2000) | most types | Bag, logs | Sawdust, straw, logs |  | 24 to 30 | 25 to 40 | 95 - 100 | 12 to 20 | 5 to 10 | 90 - 100 | 21 to 30 | 5 to 7 | 85 - 90 | 35-57 | hardwood and softwood possible
[6 empty] | (Stamets, 2000) | (Stamets, 2000) |  | (Stamets, 2000) |  |  | (Stamets, 2000)
Air Exchanges:
Spawning: | ~ 1 per hour
Primordia: | 4 to 8
Fruiting: | 4 to 8